## README
INNOVAST — EECA 2024 EnMS STARTER PACK
C8 · ESM Register & Corrective Actions
DRAFT FOR ADAPTATION — not regulatory advice. Prepared with reference to GP/ST/No.46/2024, Act 861 and P.U.(A) 466/2024; sources last verified 18 July 2026. Only Suruhanjaya Tenaga can determine compliance with the Act. · Innovast Sdn Bhd · Licensed ESCO · ESCO 327(2023)/76/2024 · www.innovast.asia · anslem@innovast.asia
How to use this register
1. Sheet 'ESM Register': one row per energy saving measure, cradle to grave — Proposed → In Progress → Completed (or Rejected). Category, type and status follow GP/ST/No.45/2024 para. 4.1.9 so the annual EE&C report is a filter of this sheet, not a rewrite.
2. Sheet 'Corrective Actions': non-conformance log per GP46 para. 7.5 — procedure breaches, underperforming measures, data gaps.
Yellow fill = enter your data. White formula cells (SPP) compute automatically — do not overtype. Example row 1 shows the format — replace it.
3. SPP = Investment cost ÷ Yearly savings cost (GP45 Equation 3). Enter NPV/IRR for board-level measures and record the discount rate in Notes.
4. Every ESM carries an M&V plan (GP46 para. 7.6): approach (e.g. IPMVP Option A/B/C/D), boundary, baseline adjustments, records location. Verified savings supersede estimates once measured.
5. Review at every Committee meeting (≥4/yr); reconcile statuses before each EE&C report. Companion: C8 Action Plan & ESM Register (docx) explains each field.

## ESM Register
INNOVAST — EECA 2024 EnMS STARTER PACK
C8 · Energy Saving Measures — action plan register
GP46 para. 6 (strategies, timelines, savings, financial analysis, roles) + para. 7.6 (M&V per ESM). Categories/types per GP45 para. 4.1.9.
ESM ID | Description | SEU / system | Category (GP45) | Type (GP45) | Status (GP45) | Est. savings (GJ/yr) | Est. savings (RM/yr) | Investment (RM) | SPP (yrs) | NPV (RM) | IRR (%) | Owner | Resources / external parties | Start | Target completion | M&V approach (IPMVP option) | M&V records location | Verified savings (GJ/yr) | Verified savings (RM/yr)
ESM-001 | Chilled water supply temperature reset +1.0°C with condenser water reset | Chiller plant | Operation | Air conditioner / chiller / AHU / cooling tower | In Progress | 950 | 98000 | 15000 |  |  |  | Facilities Engineer | Controls contractor | Aug-26 | Oct-26 | IPMVP Option C | EnMS file > M&V > ESM-001

## Corrective Actions
INNOVAST — EECA 2024 EnMS STARTER PACK
C8 · Non-conformance & corrective action log (GP46 para. 7.5)
Raise a row for any procedure breach, underperforming ESM, or data non-conformance. Close with cause, action and verification.
CA ID | Date raised | Non-conformance description | Related ESM / procedure | Root cause | Corrective / preventive action | Owner | Due | Status (Open/Closed) | Closure evidence
CA-001 | Aug-26 | Chiller plant run manually overnight against schedule, 3 nights